## RABillBrowse_Contwise6388489880
Contractor RA Bill
UMA PANORUMA VILLAS
Page 1 of 1
Total Records: 64 Records 1 To 64
Contractor | WO NO | RA Bill | RA Bill Date | Voucher_No | Project | Labour_Name | TASK | Revision | Qty | Unit | Rate | Payment Schedule | PS % | Retaintion | Retention_amt | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Net Amount | Status | Credits | Debits | TDS_Amt
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 442 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 60554 | NON GST | 0 | 60554 | 60554 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 502.75 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 68876.75 | NON GST | 0 | 68876.75 | 68876.75 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 406.5 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 55690.5 | NON GST | 0 | 55690.5 | 55690.5 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 553 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 75761 | NON GST | 0 | 75761 | 75761 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 502.75 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 68876.75 | NON GST | 0 | 68876.75 | 68876.75 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 406.5 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 55690.5 | NON GST | 0 | 55690.5 | 55690.5 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 553 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 75761 | NON GST | 0 | 75761 | 75761 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 502.75 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 68876.75 | NON GST | 0 | 68876.75 | 68876.75 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 406.5 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 55690.5 | NON GST | 0 | 55690.5 | 55690.5 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 52 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 45 | 2025-03-28 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 51 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 47 | 2025-03-28 |  | UMA PANORUMA VILLAS | shuttering,barbending and concrete works | STP Shuttering barbending and Concrete w | 0 | 600 | SFT | 245 | 100 percent on competition | 100 | 0 | 0 | 147000 | NON GST | 0 | 147000 | 147000 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | shuttering,barbending and concrete works | STP Shuttering barbending and Concrete w | 0 | 326 | SFT | 245 | 100 percent on competition | 100 | 0 | 0 | 79870 | NON GST | 0 | 79870 | 79870 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 500 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 68500 | NON GST | 0 | 68500 | 68500 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 440 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 60280 | NON GST | 0 | 60280 | 60280 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 400 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 54800 | NON GST | 0 | 54800 | 54800 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 400 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 54800 | NON GST | 0 | 54800 | 54800 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 400 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 54800 | NON GST | 0 | 54800 | 54800 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 400 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 54800 | NON GST | 0 | 54800 | 54800 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 400 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 54800 | NON GST | 0 | 54800 | 54800 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 480 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 65760 | NON GST | 0 | 65760 | 65760 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 52 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 200 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 27400 | NON GST | 0 | 27400 | 27400 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 52 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 300 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 41100 | NON GST | 0 | 41100 | 41100 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 200 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 27400 | NON GST | 0 | 27400 | 27400 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 100 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 13700 | NON GST | 0 | 13700 | 13700 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 110 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 15070 | NON GST | 0 | 15070 | 15070 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 120 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 16440 | NON GST | 0 | 16440 | 16440 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 52 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 52 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 120 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 16440 | NON GST | 0 | 16440 | 16440 | Unapproved | 0 | 0 | 0
GOPI | 6 | 48 | 2025-04-11 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 51 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 300 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 41100 | NON GST | 0 | 41100 | 41100 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 52 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 320 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 43840 | NON GST | 0 | 43840 | 43840 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 52 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 350 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 47950 | NON GST | 0 | 47950 | 47950 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 51 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 300 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 41100 | NON GST | 0 | 41100 | 41100 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 350 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 47950 | NON GST | 0 | 47950 | 47950 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 300 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 41100 | NON GST | 0 | 41100 | 41100 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 300 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 41100 | NON GST | 0 | 41100 | 41100 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 250 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 34250 | NON GST | 0 | 34250 | 34250 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - SECOND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 300 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 41100 | NON GST | 0 | 41100 | 41100 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 200 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 27400 | NON GST | 0 | 27400 | 27400 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 48 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 250 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 34250 | NON GST | 0 | 34250 | 34250 | Unapproved | 0 | 0 | 0
GOPI | 6 | 53 | 2025-04-29 |  | UMA PANORUMA VILLAS | shuttering,barbending and concrete works | STP Shuttering barbending and Concrete w | 0 | 220 | SFT | 245 | 100 percent on competition | 100 | 0 | 0 | 53900 | NON GST | 0 | 53900 | 53900 | Unapproved | 0 | 0 | 0
GOPI | 6 | 63 | 2025-05-09 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 52 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 280 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 38360 | NON GST | 0 | 38360 | 38360 | Unapproved | 0 | 0 | 0
GOPI | 6 | 63 | 2025-05-09 |  | UMA PANORUMA VILLAS | shuttering,barbending and concrete works | STP Shuttering barbending and Concrete w | 0 | 146 | SFT | 245 | 100 percent on competition | 100 | 0 | 0 | 35770 | NON GST | 0 | 35770 | 35770 | Unapproved | 0 | 0 | 0
GOPI | 6 | 63 | 2025-05-09 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 250 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 34250 | NON GST | 0 | 34250 | 34250 | Unapproved | 0 | 0 | 0
GOPI | 6 | 63 | 2025-05-09 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 63 | 2025-05-09 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 52 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 250 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 34250 | NON GST | 0 | 34250 | 34250 | Unapproved | 0 | 0 | 0
GOPI | 6 | 63 | 2025-05-09 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 51 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 150 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 20550 | NON GST | 0 | 20550 | 20550 | Unapproved | 0 | 0 | 0
GOPI | 6 | 63 | 2025-05-09 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 48 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 300 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 41100 | NON GST | 0 | 41100 | 41100 | Unapproved | 0 | 0 | 0
GOPI | 6 | 76 | 2025-06-07 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 350 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 47950 | NON GST | 0 | 47950 | 47950 | Unapproved | 0 | 0 | 0
GOPI | 6 | 76 | 2025-06-07 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 46 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 350 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 47950 | NON GST | 0 | 47950 | 47950 | Unapproved | 0 | 0 | 0
GOPI | 6 | 76 | 2025-06-07 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 250 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 34250 | NON GST | 0 | 34250 | 34250 | Unapproved | 0 | 0 | 0
GOPI | 6 | 76 | 2025-06-07 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 45 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 250 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 34250 | NON GST | 0 | 34250 | 34250 | Unapproved | 0 | 0 | 0
GOPI | 6 | 76 | 2025-06-07 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 250 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 34250 | NON GST | 0 | 34250 | 34250 | Unapproved | 0 | 0 | 0
GOPI | 6 | 76 | 2025-06-07 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 44 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 250 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 34250 | NON GST | 0 | 34250 | 34250 | Unapproved | 0 | 0 | 0
GOPI | 6 | 76 | 2025-06-07 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 51 - FIRST FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 650 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 89050 | NON GST | 0 | 89050 | 89050 | Unapproved | 0 | 0 | 0
GOPI | 6 | 76 | 2025-06-07 |  | UMA PANORUMA VILLAS | Brick Work And Plastering Works | 48 - GROUND FLOOR BRICK WORK AND PLASTERING WORKS | 0 | 250 | SFT | 137 | 100 percent on competition | 100 | 0 | 0 | 34250 | NON GST | 0 | 34250 | 34250 | Unapproved | 0 | 0 | 0
GOPI | 6 | 77 | 2025-06-07 |  | UMA PANORUMA VILLAS | Shuttering and rod bending works stp | STP Shuttering barbending and Concrete w | 0 | 0.76 | NO | 637711 | 100 percent on competition | 100 | 0 | 0 | 484660.36 | NON GST | 0 | 484660.36 | 484660.36 | Unapproved | 0 | 0 | 0