## Sheet1
Sr No | Client Name | City | 1st Incharge | 2nd Incharge | Status | Description | Target Date | PO Hand Over | [8 empty] | Type Of Installation | Company Type | First Time User | Previous Vendor | Welcome Mail Date | Project KickOff Meeting Date | Act. PO Date | As Per PO Module Name | Module wise Owners |  |  |  | Software Installation |  |  |  | Training Calender Snd Dt. | Highrise Training |  |  |  |  | Practice Session |  |  |  |  | Master Data Entry / Data Migration |  |  |  |  | Pilot Project Implementation |  |  |  |  | Implementation Signoff |  | Hand Over to Support
[8 empty] | Payment Shedule | % | Amount | Received Date | Received Amount | Balance Amount | Rec. PO Date | Soft Commitments | Status | [8 empty] | Emploee Name | Contact No. | Department | Responsobility | Start Date | End Date | Status | If Not Reason |  | Start Date | End Date | Status | SignOff Date | If Not Reason | Start Date | End Date | Status | SignOff Date | If Not Reason | Start Date | End Date | Status | SignOff Date | If Not Reason | Start Date | End Date | Status | SignOff Date | If Not Reason | SignOff Date | If Not Reason
2 | D & A Property Developers Pvt. Ltd. (Shapurjee) | Mumbai | Akshay | Amey | Pracitce | Data migration is going on | 2023-06-30 | Along with Purchase Order | 20 | 59900 |  |  | 59900 | 2023-02-22 |  |  | Cloud - Go4Hosting Data Center, CyFuture India Private Limited. | Real Estate Builders | Yes | NA | 2023-02-23 | 2023-03-10 |  |  | Avijit Upadhyay | 98201 45501 | Business Head | [5 empty] | 2023-03-04
[13 empty] | 0 | [11 empty] | Nilay Thakur | 97697 38951 | Project Head
[13 empty] | 0 | [10 empty] | Engineering Module |  |  |  |  | 2023-06-03 | 2023-10-03 | Complete |  |  | 15/3/2023 | 15/3/2023 | Complete
[8 empty] | At the Installation of Base Product | 40 | 119800 |  |  | 119800 | [10 empty] | Purchase Module |  |  |  |  | 2023-06-03 | 2023-10-03 | Complete |  |  | 15/3/2023 | 15/3/2023 | Complete
[13 empty] | 0 | [10 empty] | Contracts Module |  |  |  |  | 2023-06-03 | 2023-10-03 | Complete |  |  | 16/3/2023 | 16/3/2023 | Complete
[13 empty] | 0 | [10 empty] | Site Module |  |  |  |  | 2023-06-03 | 2023-10-03 | Complete |  |  | 16/3/2023 | 16/3/2023 | Complete
[8 empty] | At the completion of Classroom Training | 25 | 74875 |  |  | 74875 | [10 empty] | Sales Module |  |  |  |  | 2023-06-03 | 2023-10-03 | Complete |  |  | 16/3/2023 | 16/3/2023 | Complete
[13 empty] | 0 | [10 empty] | Accounts Module |  |  |  |  | 2023-06-03 | 2023-10-03 | Complete |  |  | 20/3/2023 | 20/3/2023 | Complete
[13 empty] | 0 | [10 empty] | Work Flow Module |  |  |  |  | 2023-06-03 | 2023-10-03 | Complete
[8 empty] | At the start of Go- Live | 15 | 44925 |  |  | 44925 | [10 empty] | Dashboard |  |  |  |  | 2023-06-03 | 2023-10-03 | Complete
[13 empty] | 0 | [10 empty] | Admin Tool |  |  |  |  | 2023-06-03 | 2023-10-03 | Complete
[13 empty] | 0 | [10 empty] | MIS | NA
[13 empty] | 0 | [10 empty] | Customer Portal | NA
[13 empty] | 0 | [10 empty] | Quality Check App | NA
[13 empty] | 0 | [10 empty] | Workflow App | NA
[8 empty] | Total |  | 299500 |  | 0 | 299500
4 | Dynamic Realty | Pune | Akshay | Akshay | Go Live Started. | Go Live Started, Need some customization in dashboard and Reports module. Last two stages payment pending. | 2023-06-30 | Along with Purchase Order | 20 | 0 |  |  | 0 | 44813 |  |  | Kanix cloud server | Real State Builder | No | Newton's ERP | 2022-09-28 | 2022-11-08 |  |  | Yogesh Mhaske | 9922225713 |  | Manager | 44869 | 44876 | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[13 empty] | 0 | [17 empty] | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Engineering Module | Amol Sole | 8698698169 | Engineering |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[8 empty] | At the Installation of Base Product | 40 | 0 |  |  | 0 | [10 empty] | Purchase Module | Nitin.J | 9890212081 | Purchase |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Contracts Module | Amol Sole/Shavin.S | 8698698169 | Contracts |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Site Module | Yogesh Mhaske | 9922225713 | Site |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[8 empty] | At the completion of Classroom Training | 25 | 0 |  |  | 0 | [9 empty] | 2023-03-27 | Sales Module |  |  |  |  | 2023-04-01 | 2023-04-04 | Completed |  |  | 2023-04-18 | 2023-04-18 | Completed |  |  | 2023-04-18 | 2023-05-18 | Completed |  |  | 2023-05-01 | [10 empty] | Not received signoff
[13 empty] | 0 | [9 empty] | 2023-03-27 | Marketing Module |  |  |  |  | 2023-04-01 | 2023-04-04 | Completed |  |  | 2023-04-19 | 2023-04-19 | Completed |  |  | 2023-04-19 | 2023-05-19 | Completed |  |  | 2023-05-01 | [10 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Accounts Module | [6 empty] | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[8 empty] | At the start of Go- Live | 15 | 0 |  |  | 0 | [9 empty] | 2023-03-27 | Dashboard | Akshay Sonar | 9930107287 | Director |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[13 empty] | 0 | [9 empty] | 2023-03-27 | MIS | [6 empty] | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[13 empty] | 0 | [9 empty] | 2023-03-27 | Admin Tool | Amol Sole | 8698698169 | Billing |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Customer Portal | [6 empty] | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Quality Check App | [6 empty] | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Workflow App | [6 empty] | Completed |  |  |  |  | Completed |  |  |  |  | Completed | [13 empty] | Not received signoff
[8 empty] | Total |  | 0 |  | 0 | 0
9 | Lotus Group | Pune | Akshay | Ankush | Go live Start | Training Completed. Go Live Started | 2023-06-15 | Along with Purchase Order | 10 | 105000 |  |  | 105000 | 2022-11-21 |  |  |  | Real Estate Builders | NO | StartegicERP | 2022-11-21 | 2023-01-10 |  |  | Amit Chajjed | 9823336161 | Sr. Manager | [5 empty] | 2023-01-05
[13 empty] | 0 | [11 empty] | Ashtami | 7757069504 | Account
[13 empty] | 0 | [10 empty] | Engineering Module | Pankaj | 9158776888 | Co-ordinator |  | 2023-01-01 | 2023-01-05 | Done |  |  | 2023-01-12 | 2023-01-12 | Complete |  |  | 2023-01-12 | 13/03/2023 | Completed | [7 empty] | 15/03/2023
[8 empty] | At the Installation of Base Product | 40 | 420000 |  |  | 420000 | [10 empty] | Purchase Module |  |  |  |  | 2023-01-01 | 2023-01-05 | Done |  |  | 2023-01-13 | 2023-01-13 | Complete |  |  | 2023-01-13 | 13/03/2023 | Completed | [7 empty] | 15/03/2023
[13 empty] | 0 | [10 empty] | Contracts Module |  |  |  |  | 2023-01-01 | 2023-01-05 | Done |  |  | 2023-01-16 | 2023-01-16 | Complete |  |  | 2023-01-16 | 13/03/2023 | Completed | [7 empty] | 15/03/2023
[13 empty] | 0 | [10 empty] | Site Module |  |  |  |  | 2023-01-01 | 2023-01-05 | Done |  |  | 2023-01-13 | 2023-01-13 | Complete |  |  | 2023-01-13 | 13/03/2023 | Completed | [7 empty] | 15/03/2023
[8 empty] | At the completion of Classroom Training | 25 | 262500 |  |  | 262500 | [10 empty] | Sales Module |  |  |  |  | 2023-01-01 | 2023-01-05 | Done |  |  | 2023-01-10 | 2023-01-10 | Complete |  |  | 2023-01-10 | 15/02/2023 | Completed |  |  | 15/02/2023 | 20/02/2023 | Done |  |  | 20/02/2023
[13 empty] | 0 | [10 empty] | Marketing Module |  |  |  |  | 2023-01-01 | 2023-01-05 | Done |  |  | 2023-01-11 | 2023-01-11 | Complete |  |  | 2023-01-11 | 15/02/2023 | Completed |  |  | 15/02/2023 | 20/02/2023 | Done |  |  | 20/02/2023
[13 empty] | 0 | [10 empty] | Accounts Module |  |  |  |  | 2023-01-01 | 2023-01-05 | Done |  |  | 2023-01-17 | 2023-01-17 | Complete |  |  | 2023-01-17 | 13/03/2023 | Completed | [7 empty] | 15/03/2023
[8 empty] | At the start of Go- Live | 25 | 262500 |  |  | 262500 | [10 empty] | Dashboard |  |  |  |  | 2023-01-01 | 2023-01-05 | Done | [17 empty] | 15/03/2023
[13 empty] | 0 | [10 empty] | Admin Tool |  |  |  |  | 2023-01-01 | 2023-01-05 | Done |  |  | 2023-01-17 | 2023-01-17 | Complete |  |  | 2023-01-17 | 2023-01-17 | Completed | [7 empty] | 15/03/2023
[13 empty] | 0 | [10 empty] | MIS | NA | [23 empty] | 15/03/2023
[13 empty] | 0 | [10 empty] | Customer Portal | NA | [23 empty] | 15/03/2023
[13 empty] | 0 | [10 empty] | Quality Check App | NA
[13 empty] | 0 | [10 empty] | Workflow App | NA
[8 empty] | Total |  | 1050000 |  | 0 | 1050000
13 | MDP Infra | Gwalior | Akshay | Amey | GO Live started | Go Live Signoff Pending | 2023-04-15 | Along with Purchase Order | 20 | 0 |  |  | 0 | 2023-02-22 | [10 empty] | Avijit Upadhyay | 98201 45501 | Business Head
[13 empty] | 0 | [11 empty] | Nilay Thakur | 97697 38951 | Project Head
[13 empty] | 0 | [10 empty] | Engineering Module
[8 empty] | At the Installation of Base Product | 40 | 0 |  |  | 0 | [10 empty] | Purchase Module
[13 empty] | 0 | [10 empty] | Contracts Module
[13 empty] | 0 | [10 empty] | Site Module
[8 empty] | At the completion of Classroom Training | 25 | 0 |  |  | 0 | [10 empty] | Sales Module
[13 empty] | 0 | [10 empty] | Accounts Module
[13 empty] | 0 | [10 empty] | Work Flow Module
[8 empty] | At the start of Go- Live | 15 | 0 |  |  | 0 | [10 empty] | Dashboard
[13 empty] | 0 | [10 empty] | MIS
[13 empty] | 0 | [10 empty] | Admin Tool
[13 empty] | 0 | [10 empty] | Customer Portal
[13 empty] | 0 | [10 empty] | Quality Check App
[13 empty] | 0 | [10 empty] | Workflow App
[8 empty] | Total |  | 0 |  | 0 | 0
14 | Mihir Group | Pune | Akshay | Ankush | Go live Start | Training Completed. Go Live Started | 2023-04-15 | Along with Purchase Order | 60 | 720000 |  |  | 720000 | 2022-02-11 |  |  |  | Real Estate Builders | YES |  | 2022-02-11 | 2023-01-10 |  |  | Vedant Sabadra | 8149699900 | Sr. Manager | [5 empty] | 2023-11-10
[13 empty] | 0 | [11 empty] | Rakesh | 7776906407 | Co-ordinator
[13 empty] | 0 | [10 empty] | Engineering Module |  |  |  |  | 2023-11-07 | 2023-11-11 | Done |  |  | 2023-01-23 | 2023-01-23 | Complete |  |  | 2023-01-23 | 2023-02-15 | Completed | [7 empty] | 2023-02-15
[8 empty] | On 35 days of PO | 40 | 480000 |  |  | 480000 | [10 empty] | Purchase Module |  |  |  |  | 2023-11-07 | 2023-11-11 | Done |  |  | 2023-01-24 | 2023-01-24 | Complete |  |  | 2023-01-24 | 2023-02-15 | Completed | [7 empty] | 2023-02-15
[13 empty] | 0 | [10 empty] | Contracts Module |  |  |  |  | 2023-11-07 | 2023-11-11 | Done |  |  | 2023-03-21 | 2023-03-21 | Complete |  |  | 2023-02-21 | 2023-02-21 | Completed | [7 empty] | 2023-02-21
[13 empty] | 0 | [10 empty] | Site Module |  |  |  |  | 2023-11-07 | 2023-11-11 | Done |  |  | 2023-01-23 | 2023-01-23 | Complete |  |  | 2023-01-23 | 2023-02-15 | Completed | [7 empty] | 2023-02-15
[8 empty] | At the completion of Classroom Training | 0 |  |  |  | 0 | [10 empty] | Sales Module |  |  |  |  | 2023-11-07 | 2023-11-11 | Done | [6 empty] | Client can't schedule meeting for training | [5 empty] | 2022-11-10 | 2022-12-15 | Complete | 2022-12-15
[13 empty] | 0 | [10 empty] | Marketing Module |  |  |  |  | 2023-11-07 | 2023-11-11 | Done | [6 empty] | Client can't schedule meeting for training | [5 empty] | 2022-11-10 | 2022-12-15 | Complete | 2022-12-15
[13 empty] | 0 | [10 empty] | Accounts Module |  |  |  |  | 2023-11-07 | 2023-11-11 | Done |  |  | 2023-03-06 | 2023-03-06 | Complete |  |  | 2023-03-06 | 2023-03-20 | Completed | [7 empty] | 2023-03-20
[8 empty] | At the start of Go- Live | 0 |  |  |  | 0 | [10 empty] | Dashboard |  |  |  |  | 2023-11-07 | 2023-11-11 | Done |  |  | 2023-03-06 | 2023-03-06 | Complete
[13 empty] | 0 | [10 empty] | Admin Tool |  |  |  |  | 2023-11-07 | 2023-11-11 | Done |  |  | 2023-01-23 | 2023-01-23 | Complete |  |  | 2023-01-23 | 2023-01-23 | Completed | [7 empty] | 2023-01-23
[13 empty] | 0 | [10 empty] | Workflow |  |  |  |  | 22/03/2023 |  | Testing Pending
[13 empty] | 0 | [10 empty] | Customer Portal | NA
[13 empty] | 0 | [10 empty] | Quality Check App | NA
[13 empty] | 0 | [10 empty] | Workflow App | NA
[8 empty] | Total |  | 1200000 |  | 0 | 1200000
36 | Texture Concepts | Mumbai | Akshay | Supriya | Practice |  | 2023-04-30 | Along with Purchase Order | 20 | 0 |  |  | 0 | 2023-02-22 | [10 empty] | Avijit Upadhyay | 98201 45501 | Business Head
[13 empty] | 0 | [11 empty] | Nilay Thakur | 97697 38951 | Project Head
[13 empty] | 0 | [10 empty] | Engineering Module | [29 empty] | 27/05/2023 | Complete
[8 empty] | At the Installation of Base Product | 40 | 0 |  |  | 0 | [10 empty] | Purchase Module | [29 empty] | 27/05/2023 | Complete
[13 empty] | 0 | [10 empty] | Contracts Module | [29 empty] | 27/05/2023 | Complete
[13 empty] | 0 | [10 empty] | Site Module | [29 empty] | 27/05/2023 | Complete
[8 empty] | At the completion of Classroom Training | 25 | 0 |  |  | 0 | [10 empty] | Sales Module | [29 empty] | 27/05/2023 | Complete
[13 empty] | 0 | [10 empty] | Accounts Module | [29 empty] | 27/05/2023 | Complete
[13 empty] | 0 | [10 empty] | Work Flow Module | [29 empty] | 27/05/2023 | Complete
[8 empty] | At the start of Go- Live | 15 | 0 |  |  | 0 | [10 empty] | Dashboard
[13 empty] | 0 | [10 empty] | MIS
[13 empty] | 0 | [10 empty] | Admin Tool
[13 empty] | 0 | [10 empty] | Customer Portal
[13 empty] | 0 | [10 empty] | Quality Check App
[13 empty] | 0 | [10 empty] | Workflow App
[8 empty] | Total |  | 0 |  | 0 | 0
37 | Unique Spaces | Pune | Akshay | Amey | Go Live | Account Module Go Live Pending. QC App go live pending.100% payment received. AMC is pending. | 2023-04-25 | Along with Purchase Order | 20 | 0 |  |  | 0 | 2021-03-25 |  |  | Client Server | Real State Builder | Yes | NA | NA | NA |  |  |  |  | Business Head | [27 empty] | Not received signoff
[13 empty] | 0 | [13 empty] | Project Manager | [27 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Engineering Module | Mr. Sanket Agrawal | 9881969995 | Engineer | Director | [26 empty] | Not received signoff
[8 empty] | At the Installation of Base Product | 40 | 0 |  |  | 0 | [10 empty] | Purchase Module | Mr. Sanket Agrawal | 9881969995 | Purchase | Purchase Department | [26 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Contracts Module | Mr. Sanket Agrawal | 9881969995 | Contracts | Project Management | [26 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Site Module | Mr. Sanket Agrawal | 9881969995 | Site | Project Management | [26 empty] | Not received signoff
[8 empty] | At the completion of Classroom Training | 25 | 0 |  |  | 0 | [10 empty] | Sales Module | Mr. Sanket Agrawal | 9881969995 |  | CRM Management | [26 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Accounts Module | Mr. Sanket Agrawal | 9881969995 | Accounts | Finance Management | [26 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Work Flow Module | Mr. Sanket Agrawal | 9881969995 | [28 empty] | Not received signoff
[8 empty] | At the start of Go- Live | 15 | 0 |  |  | 0 | [10 empty] | Dashboard | Mr. Sanket Agrawal | 9881969995 | [28 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | MIS | Mr. Sanket Agrawal | 9881969995 | [28 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Admin Tool | Mr. Sanket Agrawal | 9881969995 | Project Manager | [27 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Customer Portal | Mr. Sanket Agrawal | 9881969995 | [28 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Quality Check App | Mr. Sanket Agrawal | 9881969995 | [28 empty] | Not received signoff
[13 empty] | 0 | [10 empty] | Workflow App | Mr. Sanket Agrawal | 9881969995 | [28 empty] | Not received signoff
[8 empty] | Total |  | 0 |  | 0 | 0
47 | Managalam Landmark | Pune | Akshay | Ankush | Go Live Dine | HR Module Go live is pending | 2023-04-15 | Along with Purchase Order | 50 | 425000 |  |  | 425000 | 18/06/2023 |  |  |  | Real Estate Builders | Yes | NA | 19/06/2022 | 2022-02-08 |  |  | Subhash Sakore | 9011075687 | Sr. Management | [5 empty] | 27/7/2022
[13 empty] | 0 | [11 empty] | Kishor Chincolkar | 9822680600 | Purchase Head
[13 empty] | 0 | [10 empty] | Engineering Module | Rohit |  | Erp Coordinator |  | 22/7/2022 | 30/7/2022 | Complete |  |  | 2022-02-08 | 15/8/2022 | Complete |  |  | 15/8/2022 | 30/09/2022 | Complete |  |  | 15/8/2022 | 30/8/2022 | Complete |  |  | 30/8/2022 | 30/9/2022 | Complete |  |  | 2022-10-06
[8 empty] | After 45 days of installation | 25 | 212500 |  |  | 212500 | [10 empty] | Purchase Module |  |  |  |  | 22/7/2022 | 30/7/2022 | Complete |  |  | 2022-03-08 | 15/8/2022 | Complete |  |  | 15/8/2022 | 30/09/2022 | Complete |  |  | 15/8/2022 | 30/8/2022 | Complete |  |  | 30/8/2022 | 30/9/2022 | Complete |  |  | 2022-10-06
[13 empty] | 0 | [10 empty] | Contracts Module |  |  |  |  | 22/7/2022 | 30/7/2022 | Complete |  |  | 2022-04-08 | 15/8/2022 | Complete |  |  | 15/8/2022 | 30/09/2022 | Complete |  |  | 15/8/2022 | 30/8/2022 | Complete |  |  | 30/8/2022 | 30/9/2022 | Complete |  |  | 2022-10-06
[13 empty] | 0 | [10 empty] | Site Module |  |  |  |  | 22/7/2022 | 30/7/2022 | Complete |  |  | 2022-05-08 | 15/8/2022 | Complete |  |  | 15/8/2022 | 30/09/2022 | Complete |  |  | 15/8/2022 | 30/8/2022 | Complete |  |  | 30/8/2022 | 30/9/2022 | Complete |  |  | 2022-10-06
[8 empty] | After 90 days of installation or pilot project go live whichever happens first | 25 | 212500 |  |  | 212500 | [10 empty] | Accounts Module |  |  |  |  | 22/7/2022 | 30/7/2022 | Complete |  |  | 2022-06-08 | 15/8/2022 | Complete |  |  | 15/8/2022 | 30/09/2022 | Complete |  |  | 15/8/2022 | 30/8/2022 | Complete |  |  | 30/8/2022 | 30/9/2022 | Complete |  |  | 2022-10-06
[13 empty] | 0 | [10 empty] | Admin Tool |  |  |  |  | 22/7/2022 | 30/7/2022 | Complete |  |  | 2022-03-08 | 15/8/2022 | Complete |  |  | 15/8/2022 | 30/09/2022 | Complete |  |  | 15/8/2022 | 30/8/2022 | Complete |  |  | 30/8/2022 | 30/9/2022 | Complete |  |  | 2022-10-06
[13 empty] | 0 | [10 empty] | HR |  |  |  |  | 22/7/2022 | 30/7/2022 | Complete |  |  | 20/09/2022 | 20/09/2022 | Complete |  |  | 20/09/2022 | [11 empty] | Pending |  | HR Rule Configuration pending | Pending | HR Rule Configuration pending
[8 empty] | At the start of Go- Live | 0 | 0 |  |  | 0 | [10 empty] | Dashboard |  |  |  |  | 22/7/2022 | 30/7/2022 | Complete |  |  | 20/09/2022 | 20/09/2022 | Complete |  |  | 20/09/2022 | 20/09/2022 | Complete
[13 empty] | 0 | [10 empty] | Sales Module | NA
[13 empty] | 0 | [10 empty] | MIS | NA
[13 empty] | 0 | [10 empty] | Customer Portal | NA
[13 empty] | 0 | [10 empty] | Quality Check App | NA
[13 empty] | 0 | [10 empty] | Workflow App | NA
[8 empty] | Total |  | 850000 |  | 0 | 850000