## 1Quality Check63735523035550484
| Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7
Task_Name | QC_Name | QC_Description | Doc_id | Checked_by | Chk_Date | Status | Remark
102 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 01. Check basecoat waterproof completed | 1.Check basecoat waterproof is complete |  | Engineer - Elite | 2020-09-12 | Approved | completed
102 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 02. Cleaning of basecoat surface | Cleaning of basecoat surface |  | Engineer - Elite | 2020-09-12 | Approved | done
102 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 03. Check of floor piping done | Fixing of plumbing and drainage pipes and other assesories as per drawing |  | Engineer - Elite | 2020-09-12 | Approved | done
102 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 04.Availability of material for brickbat | Availability of material for bascoat i.e cement,river sand,etc. |  | Engineer - Elite | 2020-09-12 | Approved | river sand, red bricks , cement
102 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 05. Checking for mix proportion | Check for mix proportion in 1:4 |  | Engineer - Elite | 2020-09-12 | Approved | CM 1;4
102 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 06. Checking of executed brickbat work | Checking of executed brickbat work |  | Engineer - Elite | 2020-09-12 | Approved | ok
102 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 07. Checking of ponding/curing | Checking of ponding/curing minimum 3 days