## ELSR
VR EARTH MOVERS AND CONSTRUCTIONS (P) LTD
MAHINDRA WORLD CITY PUDHUVOYAL ELSR - PROGRAM SCHEDULE
TASK NAME | DURATION | START DATE | END DATE | REMARKS
SUB STRUCTURE | 129 days | 2018-10-26 | 2019-04-03
MOBILIZATION | 0 days | 2018-10-26 | 2018-10-26
RECEIPT OF DRAWINGS | 0 days | 2018-10-26 | 2018-10-26
MARKING AND SETTING OUT | 0 days | 2018-10-26 | 2018-10-26
PILING WORK | 31 days | 2018-11-27 | 2019-01-04
VERTICAL LOAD TESTING | 2 days | 2019-03-01 | 2019-03-04
EARTH WORK EXCAVATION | 5 days | 2019-03-04 | 2019-03-09
PCC FOR RAFT | 5 days | 2019-03-13 | 2019-03-19
PILE BREAKING | 1 day | 2019-03-19 | 2019-03-20
MARKING OF RAFT | 1 day | 2019-03-20 | 2019-03-21
CUTTING, BENDING AND TIENG OF REINFORCEMENT FOR RAFT AND WALL | 3 days | 2019-03-20 | 2019-03-23
SHUTTRING FOR RAFT | 2 days | 2019-03-21 | 2019-03-23
CHECKING AND CLEARANCE | 1 day | 2019-03-23 | 2019-03-24
RAFT CONCRETING | 1 day | 2019-04-02 | 2019-04-03
SUPER STRUCTURE | 105 days | 2019-04-04 | 2019-07-18
WALL STRATER MARKING | 1 day | 2019-04-04 | 2019-04-05
WALL STRATER SHUTTER FIXING AND CONCRETING | 2 days | 2019-04-05 | 2019-04-07
WALL REINFORCEMENT TIENG 1ST LIFT-`1.2RM | 2 days | 2019-04-19 | 2019-04-20
WALL BOARD MAKING FOR ELSR | 2days | 2019-04-22 | 2019-04-23
WALL SHUTTERING & SCAFFOLDING 1st LIFT | 2 days | 2019-04-23 | 2019-04-24
WALL CONCRETING 1ST LIFT | 1 day | 2019-04-25 | 2019-04-25
WALL REINFORCEMENT TIENG 2nd LIFT | 2 days | 2019-04-26 | 2019-04-27
WALL SHUTTERING & SCAFFOLDING 2nd LIFT | 2 days | 2019-04-27 | 2019-04-28
WALL CONCRETING 2ND LIFT | 1 day | 2019-04-29 | 2019-04-29
WALL REINFORCEMENT TIENG 3rd LIFT | 2 days | 2019-04-30 | 2019-05-02
WALL SHUTTERING & SCAFFOLDING 3rd LIFT | 2 days | 2019-05-02 | 2019-05-03
WALL CONCRETING 3RD LIFT | 1 day | 2019-05-04 | 2019-05-04
WALL REINFORCEMENT TIENG 4th LIFT | 2 days | 2019-05-05 | 2019-05-07
WALL SHUTTERING & SCAFFOLDING 4th LIFT | 2 days | 2019-05-07 | 2019-05-08
WALL CONCRETING 4TH LIFT | 1 day | 2019-05-09 | 2019-05-09
WALL REINFORCEMENT TIENG 5th LIFT | 2 days | 2019-05-10 | 2019-05-11
WALL SHUTTERING & SCAFFOLDING 5th LIFT | 2 days | 2019-05-13 | 2019-05-14
WALL CONCRETING 5TH LIFT | 1 day | 2019-05-15 | 2019-05-15
WALL REINFORCEMENT TIENG 6th LIFT | 2 days | 2019-05-16 | 2019-05-17
WALL SHUTTERING & SCAFFOLDING 6th LIFT | 2 days | 2019-05-18 | 2019-05-20
WALL CONCRETING 6TH LIFT | 1 day | 2019-05-21 | 2019-05-21
WALL REINFORCEMENT TIENG 7th LIFT | 2 days | 2019-05-22 | 2019-05-23
WALL SHUTTERING & SCAFFOLDING 7th LIFT | 2 days | 2019-05-24 | 2019-05-25
WALL CONCRETING 7TH LIFT | 1 day | 2019-05-27 | 2019-05-27
WALL REINFORCEMENT TIENG 8th LIFT | 2 days | 2019-05-28 | 2019-05-29
WALL SHUTTERING & SCAFFOLDING 8th LIFT | 2 days | 2019-05-30 | 2019-06-01
WALL CONCRETING 8TH LIFT | 1 day | 2019-06-01 | 2019-06-02
WALL REINFORCEMENT TIENG 9th LIFT | 2 days | 2019-06-03 | 2019-06-04
WALL SHUTTERING & SCAFFOLDING 9th LIFT | 2 days | 2019-06-05 | 2019-06-06
WALL CONCRETING 9TH LIFT | 1 day | 2019-06-07 | 2019-06-07
WALL REINFORCEMENT TIENG 10th LIFT | 2 days | 2019-06-08 | 2019-06-09
WALL SHUTTERING & SCAFFOLDING 10th LIFT | 2 days | 2019-06-10 | 2019-06-11
WALL CONCRETING 10TH LIFT | 1 day | 2019-06-12 | 2019-06-12
WALL REINFORCEMENT TIENG 11th LIFT | 2 days | 2019-06-13 | 2019-06-14
WALL SHUTTERING & SCAFFOLDING 11th LIFT | 2 days | 2019-06-15 | 2019-06-17
WALL CONCRETING 11TH LIFT | 1 day | 2019-06-18 | 2019-06-18
WALL REINFORCEMENT TIENG 12th LIFT | 2 days | 2019-06-20 | 2019-06-21
WALL SHUTTERING & SCAFFOLDING 12th LIFT | 2 days | 2019-06-22 | 2019-06-23
WALL CONCRETING 12TH LIFT | 1 day | 2019-06-24 | 2019-06-24
WALL REINFORCEMENT TIENG 13th LIFT | 2 days | 2019-06-25 | 2019-06-27
WALL SHUTTERING & SCAFFOLDING 13th LIFT | 2 days | 2019-06-28 | 2019-06-29
WALL CONCRETING 13TH LIFT | 1 day | 31-06-2019 | 31-06-2019
WALL REINFORCEMENT TIENG 14th LIFT | 2 days | 2019-07-01 | 2019-07-02
WALL SHUTTERING & SCAFFOLDING 14th LIFT | 2 days | 2019-07-03 | 2019-07-04
WALL CONCRETING 14TH LIFT | 1 day | 2019-07-05 | 2019-07-06
WALL REINFORCEMENT TIENG 15th LIFT | 2 days | 2019-07-08 | 2019-07-09
WALL SHUTTERING & SCAFFOLDING 15th LIFT | 2 days | 2019-07-10 | 2019-07-11
WALL CONCRETING 15TH LIFT | 1 day | 2019-07-12 | 2019-07-12
WALL REINFORCEMENT TIENG 16th LIFT | 2 days | 2019-07-13 | 2019-07-15
WALL SHUTTERING & SCAFFOLDING 16th LIFT | 2 days | 2019-07-16 | 2019-07-17
WALL CONCRETING 16TH LIFT | 1 day | 2019-07-18 | 2019-07-18
TANK ACTIVITY | 40 days | 2019-07-20 | 2019-08-31
Scaffolding for base Slab | 10 days | 2019-07-22 | 2019-07-31
Shuttering for base Slab | 07 days | 2019-08-01 | 2019-08-08
Reinforcement for Base slab | 05days | 2019-08-06 | 2019-08-12
Concreting for base slab | 1 day | 2019-08-14 | 2019-08-14
Reinforcement for inner wall | 2 days | 2019-08-16 | 2019-08-17
Shuttering for inner wall | 3 days | 2019-08-17 | 2019-08-19
Concreting for inner wall | 2 days | 2019-08-20 | 2019-08-21
Scaffolding for Cover Slab | 2 days | 2019-08-22 | 2019-08-23
Reinforcement for Cover Slab | 2 days | 2019-08-24 | 2019-08-26
Concreting for Cover Slab | 1 day | 2019-08-27 | 2019-08-27
Parapet wall Reinforcement | 1 day | 2019-08-28 | 2019-08-28
Parapet wall Shuttering | 2 day | 2019-08-28 | 2019-08-29
Parapet wall Concreting | 2 day | 2019-08-29 | 2019-08-30
FINISHING WORKS | 28 days | 2019-08-02 | 2019-08-28
WALL PLASTERING INNER | 7 days | 2019-08-02 | 2019-08-09
WALL PLASTERING OUTER | 07 days | 2019-08-05 | 2019-08-12
TANK WATERPROOFING | 3 days | 2019-08-18 | 2019-08-21
LADER FABRICATION & ERECTION | 7 days | 2019-07-20 | 2019-07-28
PAINTING | 15 days | 2019-08-16 | 2019-08-31
INNER PAINTING | 7 days | 2019-08-16 | 2019-08-23
OUTER PAINTING | 7days | 2019-08-20 | 2019-08-27
CLEANING AND HANDING OVER | 3 days | 2019-08-28 | 2019-08-31
prepared on 10-03-2019

## GLSR
MAHINDRA WORLD CITY, PUDUVOYAL Program Schedule for GLSR
TASK NAME | DURATION | START DATE | END DATE
Earth work excavation | 10 days | 2019-02-16 08:00 | 2019-02-28 08:00
Compaction and testing | 4 days | 2019-03-05 08:00 | 2019-03-09 08:00
PCC - Collection pit | 1 day | 2019-03-09 08:00 | 2019-03-11 08:00
Raft - collection pit-rebar | 1 day | 2019-03-19 17:00 | 2019-03-20 17:00
Raft - collection pit-shuttering | 1 day | 2019-03-20 17:00 | 2019-03-21 17:00
Raft - collection pit-concrete | 1 day | 2019-03-21 17:00 | 2019-03-22 17:00
wall up to base | 2 days | 2019-03-22 17:00 | 2019-03-25 17:00
hard core layer | 2 days | 2019-03-25 17:00 | 2019-03-27 17:00
PCC 1:4:8 | 2 days | 2019-04-09 08:00 | 2019-04-11 08:00
reinforcement for raft | 10 days | 2019-04-11 08:00 | 2019-04-23 08:00
shuttering for raft | 4 days | 2019-04-23 08:00 | 2019-04-27 08:00
RCC Raft concrete | 2 days | 2019-04-27 08:00 | 2019-04-30 08:00
RCC wall starter marking | 1 day | 2019-04-30 08:00 | 2019-05-02 08:00
RCC wall startrer shuttering and concreting (outer wall) | 2 days | 2019-05-02 08:00 | 2019-05-04 08:00
RCC wall startrer shuttering and concreting (inner wall) | 2 days | 2019-05-04 08:00 | 2019-05-07 08:00
RCC wall upto 1.2 Rm- rebar | 2 days | 2019-05-07 08:00 | 2019-05-09 08:00
RCC wall upto 1.2 Rm- shuttering | 3 days | 2019-05-09 08:00 | 2019-05-13 08:00
RCC wall upto 1.2 Rm- concreting | 1 day | 2019-05-13 08:00 | 2019-05-14 08:00
RCC wall upto 2.4 Rm-rebar | 2 days | 2019-05-14 08:00 | 2019-05-16 08:00
RCC wall upto 2.4 Rm-shuttering | 4 days | 2019-05-16 08:00 | 2019-05-21 08:00
RCC wall upto 2.4 Rm-concreting | 1 day | 2019-05-21 08:00 | 2019-05-22 08:00
RCC wall upto 3.55 Rm-rebar | 2 days | 2019-05-22 08:00 | 2019-05-24 08:00
RCC wall upto 3.55 Rm-shuttering | 4 days | 2019-05-24 08:00 | 2019-05-29 08:00
RCC wall upto 3.55 Rm-concreting | 1 day | 2019-05-29 08:00 | 2019-05-30 08:00
RCC wall upto 4.5Rm- rebar | 2 days | 2019-05-30 08:00 | 2019-06-01 08:00
RCC wall upto 4.5 Rm- shuttering | 5 days | 2019-06-01 08:00 | 2019-06-07 08:00
RCC wall upto 4.5 Rm- concreting | 1 day | 2019-06-07 08:00 | 2019-06-08 08:00
RCC wall upto 1.2 Rm- rebar (Outer wall) | 2 days | 2019-06-08 08:00 | 2019-06-11 08:00
RCC wall upto 1.2 Rm- shuttering | 3 days | 2019-06-11 08:00 | 2019-06-14 08:00
RCC wall upto 1.2 Rm- concreting | 1 day | 2019-06-14 08:00 | 2019-06-15 08:00
RCC wall upto 2.4 Rm-rebar | 2 days | 2019-06-15 08:00 | 2019-06-18 08:00
RCC wall upto 2.4 Rm-shuttering | 3 days | 2019-06-18 08:00 | 2019-06-21 08:00
RCC wall upto 2.4 Rm-concreting | 1 day | 2019-06-21 08:00 | 2019-06-22 08:00
RCC wall upto 3.55 Rm-rebar | 2 days | 2019-06-22 08:00 | 2019-06-25 08:00
RCC wall upto 3.55 Rm-shuttering | 3 days | 2019-06-25 08:00 | 2019-06-28 08:00
RCC wall upto 3.55 Rm-concreting | 1 day | 2019-06-28 08:00 | 2019-06-29 08:00
RCC wall upto 4.5Rm- rebar | 2 days | 2019-06-29 08:00 | 2019-07-02 08:00
RCC wall upto 4.5 Rm- shuttering | 3 days | 2019-07-02 08:00 | 2019-07-05 08:00
RCC wall upto 4.5 Rm- concreting | 1 day | 2019-07-05 08:00 | 2019-07-06 08:00
doom slab shuttering | 15 days | 2019-07-06 08:00 | 2019-07-24 08:00
doom slab reinforcement | 10 days | 2019-07-24 08:00 | 2019-08-05 08:00
doom slab concrete | 1 day | 2019-08-05 08:00 | 2019-08-06 08:00
deshuttering | 2 days | 2019-08-06 08:00 | 2019-08-08 08:00
waterproofing inner | 3 days | 2019-08-12 08:00 | 2019-08-16 08:00
wall plastering inner | 5 days | 2019-08-16 08:00 | 2019-08-22 08:00
wall plastering outer | 7 days | 2019-08-22 08:00 | 2019-08-30 08:00
grano flooring | 3 days | 2019-08-22 | 2019-08-25
plinth protection | 2 days | 2018-08-25 | 2018-08-26
cement painting out side | 2 days | 2019-08-25 | 2019-08-26
MS hand railing | 5 days | 2018-08-20 | 2018-08-25
MS grill and ladder | 5 days | 2018-08-20 | 2018-08-25
Cleaning and handing over | 5days | 2019-08-25 | 2019-08-30
prepared on 10-03-2019

## Pump House
VR EARTH MOVERS & CONSTRUCTIONS (P) LTD
MAHINDRA INDUSTRIAL PARK LTD Program schedule for Pump House
TASK NAME | DURATION | START DATE | END DATE | Remarks
Earth work excavation | 3 days | 2018-12-29 | 2019-01-03
GSB laying work | 4 days | 2019-01-03 | 2019-01-08
River sand filling | 1 day | 2019-01-08 | 2019-01-09
PCC 1:4:8 | 1 day | 2019-01-09 | 2019-01-10
R.C.C Footing reinforcement | 1 day | 2019-01-10 | 2019-01-11
R.C.C Footing shuttering | 1 day | 2019-01-11 | 2019-01-12
R.C.C Footing concrete | 1 day | 2019-02-01 | 2019-02-02
RCC column upto NGL (starter marking) | 1 day | 2019-02-07 | 2019-02-08
RCC column upto NGL (shuttering) | 1 day | 2019-02-08 | 2019-02-09
RCC column upto NGL (concreting) | 1 day | 2019-02-08 | 2019-02-09
pcc for grade beam | 1 day | 2019-02-09 | 2019-02-10
grade beam reinforcement | 2 days | 2019-02-11 | 2019-02-13
grade beam shuttering | 2 days | 2019-02-13 | 2019-02-15
Grade beam concreting | 2 days | 2019-03-02 | 2019-03-05
RCC column upto FGL (starter marking) | 1 day | 2019-03-05 | 2019-03-06
RCC column upto FGL (reinforcement) | 1 day | 2019-03-06 | 2019-03-07
RCC column upto FGL (shuttering) | 1 day | 2019-03-07 | 2019-03-08
RCC column upto FGL (concreting) | 2 days | 2019-03-07 | 2019-03-09
basement brick work | 2 days | 2019-03-10 08:00 | 2019-03-12 16:00
basement earth back filling & consolidation work | 6 days | 2019-03-13 16:00 | 2019-03-20 16:00
pcc for Plinth beam | 24 days | 2019-03-19 16:00 | 2019-04-16
plinth beam reinforcement | 2 days | 2019-03-19 16:00 | 2019-03-21 16:00
plinth beam shuttering | 2 days | 2019-04-12 | 2019-04-14
plinth beam concreting | 1 day | 2019-04-15 | 2019-04-16
RCC column upto roof level(starter marking) | 1 day | 2019-04-17 | 2019-04-18
RCC column upto roof level(reinforcement) | 5 days | 2019-04-19 | 2019-04-25
RCC column upto roof level(shuttering) | 4 days | 2019-04-23 | 2019-04-27
RCC column upto roof level(concreting) | 2 days | 2019-04-29 | 2019-05-02
basement grade salb concrete | 3 days | 2019-04-16 | 2019-04-20
Roof beam & slab shuttering work | 3 days | 2019-05-03 | 2019-05-07
Roof beam & slab reinforcement work | 3 days | 2019-05-08 | 2019-05-11
electrical conduits laying work for roof | 1 day | 2019-05-11 | 2019-05-12
Roof slab concrete | 1 day | 2019-05-13 | 2019-05-14
column above roof level | 5 days | 2019-05-14 | 2019-05-19
Roof beam &slab deshuttering | 2 days | 2019-05-22 | 2019-05-24
Flyash brickwork for parapet | 3 days | 2019-05-25 | 2019-05-29
Flyash brickwork upto lintel | 3 days | 2019-05-19 08:00 | 2019-05-22 16:00
lintel&sunshade shuttering | 2 days | 2019-05-30 | 2019-06-01
lintel&sunshade reinforcement | 2 days | 2019-06-02 08:00 | 2019-06-04 16:00
lintel & sunshade concrete | 1 day | 2019-06-05 | 2019-06-06
Flyash brickwork upto roof | 3 days | 2019-06-06 | 2019-06-09
ceiling plastering | 4 days | 2019-06-10 | 2019-06-14
inner wall plastering | 10 days | 2019-06-12 | 2019-06-23
external wall plastering | 10 days | 2019-06-22 | 2019-07-04
parapet wall inner plastering | 5 days | 2019-07-04 | 2019-07-10
weathering course | 5 days | 2019-07-10 | 2019-07-16
press tiles | 6 days | 2019-07-13 | 2019-07-20
Band plastreing | 5 days | 2019-07-19 | 2019-07-25
rain water harvesting | 15 days | 2019-07-24 | 2019-08-10
Prepared on : 10-03-2019