## Sheet1
Project Name / Bldg. Name:- Ravima Ventures - Newton Homes |  |  |  |  | Date :- 28/02/2020
Scope of Work :- POP work |  |  |  |  | Work Order No. -
Contractor :- Moin Khan |  |  |  |  | Kind Attn.:- |  |  | b
Address:-
Mob :-
Email ID-
Sr. No. | Item Description |  |  | Quantity | Rate | Unit | Amount ( Rs.)
1 | Gypsume punning work for ceilling with |  |  | As per Actual measurements
"Gyroc Xpert" , As per drawing and design. Use of fibre
| mesh and bonding agent wherever required. |  |  |  | 9.5 | Sq.Fts.
2 | Gypsume punning work for walls with
"Gyroc Xpert" , As per drawing and design. Use of fibre
| mesh and bonding agent wherever required. |  |  |  | 20.5 | Sq.Fts.
A | After completion of all wall works------------70%
B | After completion of door,window, and
skirting finishings----------------------------------20%
C | After handing over in all respect--------------10%
Specification : GYPROC ULTRA SERIES, SUPREME-68 GYPSUME, 12MM THICK 2' X 3' POP SHEETS
Completion Date : AS PER REQUIREMENT ON SITE
GENERAL TERMS & CONDITIONS :-
1 | All material should be get approved from Project In Charge before application.
2 | Measurement of actual work done shall be taken time to time jointly by company's engg. & contractor & shall be record the same in measurement sheet. Whatever be the difference in qty. of work order & actual work done shall be paid / recover after successful completion of entire work of bldg.
3 | You will keep your Engineer at site & joint measurement will be recorded in measurement book.
4 | You will clean the site after completion of work . If not cleaning charges will be debited to you.
5 | Follow all the safety precautions at site & government regulation like labour insurance, minimum wages, child labour & any type of accident in your scope.
6 | You will maintain all the required tools & tackles with proper mechanical staff.
7 | Employer will provide water & electricity at site.
8 | The employer will not be responsible for any power cut at site.
9 | You will maintain a progress bar chart & present an activity schedule to the employer before starting the work.
10 | You will submit a proper gurantee card for the work carried out.
11 | All the work will be carried out as per the direction of structural consultant. Any rework will be carried out at your cost.
12 | You will submit running bills by fortnightly.
13 | You will maintain house keeping during the work.
14 | All work shall be carried out upto the full satisfaction of Project In charge.
15 | For any reason whatsoever if the Contractor leaves the work incomplete 5% retention amount will be forfeited
16 | The Contractors shall rectify the defects noticed during the Defect Liability Period( 12 months after completion of work) at his own cost, which have occurred due to defective workmanship / material used.
PAYMENT TERMS & CONDITIONS :-
1 | Bill will be accepted for completed work only as per mentioned in payment schedule.
2 | Deduction for Retention Amount = 5% on bill amount.
3 | Deduction for TDS & other taxes as applicable.
OTHER CONDITIONS / NOTE :-
Accepted By Agency |  | Project Incharge | Chief Engineer |  | HOD-CBD |  | Director